## Sheet1
Tasks and Assignment Breakdown
| Group: | Group 5
| Team Members (and initials): | Irfan Filipovic IF, | Shane Folden, SF | Man Him Fung, MF | Mason Jones, MJ | Siqi Wang, SW
| Date this was last updated: | 2020-04-10
| Last updated by (whom): | Group
In general, you should archive a copy of this spreadsheet (with the date in the file name) before modifying it.
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1
| Establish weekly meeting schedule. Post on shared repository. | completed | Group | 2020-04-09 | 0 | 2020-04-09 | 2020-04-09 | Group | 0 | Group | 2020-04-09
| Friday Group Meeting. Outline SRS v1 skeleton. | completed | Group | 2020-04-10 | 2 to 3 | 2020-04-10 | 2020-04-10 | Group | 2 | Group | 2020-04-10
| Sunday Group Meeting. Drafting a more complete SRS v1. | completed | Group | 2020-04-12 | 2 to 3 | 2020-04-12 | 2020-04-12 | Group | 2 | Group | 2020-04-12
| Have initial meeting with client to review v1 of SRS. | not yet completed |  | 2020-04-09
| Write up summary of client meeting. Post on shared repository. | not yet completed |  | 2020-04-09
Week 2
| Generate v1 of SDS. Post on shared repository. | not yet completed | Group | 2020-04-09
| SRS v1 clean up | not yet completed | Group |  |  | 2020-04-14